## Sheet1
ID | Family | Product | Area | Event | Lesson Learned | Actions | Input from | Status
1 | Engage | v240m | Software | Customer start developing their app in an DEV mode terminal and did not validate it in a PROD mode terminal. The result is that PROD terminals has different access control that impact on how the app must store and manage files. | Customer always need to validate and perfom a QA test over PROD mode terminals before sending their app to VF customization area. | - Inform customer about reading the documentation. - Formalizing with customer that QA test must be done in PROD terminals - Definition about ADK signature | PagSeguro | Implemented
2 | Engage | All | Software | App can not performe CLTS transactions however CT is properly handled | Engage family has an special file (emv-desired. xml) for mapping kernels and features supported. This one must be part of app bundle. | - Internal guidance in order to have it delivered to new customers - Deployment team has also a validation about presence of this file in the app load | Banrisul | Implemented
3 | Engage | Dial | Software | Transaction over SDLC protocol can not be completed. | SDLC in Brazil, specially when connected to the Lyra provider, requires a special control. An patch or HF is required. | - HF and/or patch must be validated and be part of the ADK. (Lyra) | Banrisul | Implemented
4 | Engage | All | Software | Battery misinformation | Olders ADK version requieres a patch related to power supply and/or battery. Some cases terminal can not start recharging the battery whenever it is fully discharged. | Already included in new ADK version | Stone | Implemented
5 | Engage | All | Manufacturing | Time for having a full customization | Production line require about 24 minutes for load an entire customer app. It is not just customer app issue but also adk downgrade and/or update. | - Fast load is being developed by FIT | Stone / Banrisul | Under way. Felipe Aloia is the manager for this topic
6 | Engage | All | Software | Customer start developing their own app | Any Engage family requieres ADK contract signed off before starting developing the app. Workaround is not possible once ADC need to delivers SDK environment to customer. | - Define a process on how getting the contract managed per customer. - Defining inputs for releasing SDK and development | All | Implemented. PMO has a task in Gantt chart related to contract.
7 | Engage | All | Software | Packaging | Engange has a different structure for packaging. | - FIT training is defined to show it. | All
8 | Engage | v240m | Hardware | WiFi 5Ghz | It is a plus for those customers working in public areas, ex: fairs so WiFi band can be a differentiation | - Identify customer that it is a differentiation | All | Implemented
9 | Engage | v240m | Hardware | Keyboard with intenal light | Required by those customer that operate in delivery or night (restaurant, bar, etc..) | - Identify customer that it is a differentiation | All | Implemented. Product manager has this requirement for BR leads/opportunities
10 | All | All | Software | App packaging | Packaging setup to be used by SKS at Flex is different from loading it by USB | Be aware in any case where uploading via USB is required | All | Implemented. The way to create the package was already know, LL give us the advice.
11 | All | All | Software and Hardware | SLA and/or Lead Time | Need to be careful and also aware that areas has your SLA stablished | - SR need to be aligned with internal restrictions, such as: - Customizations: around 120 days (imported/resign) - after project defined. - Local resign/supplier customization: 60 days; - SKS packaging: 5 business day - Key ceremony: 10 business day | Local / Global team | Under way as some improvements on LT is being managed
12 | Engage | v240m | Hardware | Battery level | - Level for delivery - Accurancy (full charge/discharge) | Changing BOM in order to charge at least 60% of the battery | Customer / Local | Implemented. PN already defined considering battery with 80% of loading.
13 | Engage | v240m | Hardware | Battery connector | Life expectance 30 times | - Need to define/adjust the logistic operation | Local team | Under way as customers need to be advised.
14 | Engage | v240m | Software | During the customization the terminal entered in hibernate state and the custom could not be finished | NPI process improvement? New products need to have an internal analysis before considering production??
15 | All | All | Software | App is not available for production causing additional cost, financial impacts and/or line down period. | Plan B aligned with customer in order to start production with pilot verstion instead of final version. | Discussing it with customer at the beginning of the project