## Version Controll
Author | Data | Changes | Version
Mário Abegão | 2020-02-19 | First verstion | 1.0
Mário Abegão | 2020-03-02 | Review | 1.1
Mário Abegão | 2020-07-13 | Review and alignment with BSC Project Control | 1.2
Mário Abegão | 2020-08-11 | Review | 1.3

## Risks
Low Impact
Medium Impact
| High Impact |  | next ID: | 10
ID | Area | Description | Probability | Impact | Risk | Prob. Rev | Imp. Rev | Risk. Rev. | Result | Action | Owner | Responsible | Status | Comments
7 | Pilot | Plan to start it can be impacted by covid-19 | 4 | 4 | 16 | 2 | 4 | 8 | Delay on SR | Start negotiation the plan in advance with customer. May be some merchants can be changed in order to receive the terminals | Mauricio Bonifacino | Mário Abegão / Marcos Botelho | Opened | 13/07: First cycle need to be completed in order to start discussing it. 07/08: After discussing with customer he is not considering it as a road block eventhough the risk still exists (second wave eg.)
3 | Development | Safra env is not stable | 4 | 4 | 16 | 3 | 4 | 12 | Impact and delay for certification | Constantly check and inform the status env to Safra managers | Mauricio Bonifacino / Eduardo Quevedo | Mário Abegão / Edson Nascimento | Mitigated | 02/03: Even after lots of scalation the environment is still presenting instability 13/07: Safra is being more responsive than in the past however the env keep being not stable. Also Safra is supporting us for ELO, ALELO and TICKET certification cause of COVID-19
6 | Certification | Budget overcoming | 4 | 3 | 12 | 4 | 3 | 12 | Budget demand is higher than planed | Tracking activities closely and trying to get parallel execution | Mauricio Bonifacino | Mário Abegão / Edson Nascimento | Mitigated | 13/07: Dailly meeting with Argotechno
8 | Development | New features implemented by Safra while the cert is happening | 4 | 4 | 16 | 4 | 3 | 12 | Delay on SR | Meeting with customer (Daniel Lucats) already done. At the end of cycle 1/2 the difference will be evaluated together, may be a waiver is accepted. | Mauricio Bonifacino | Mário Abegão / Edson Nascimento | Mitigated | 13/07: By now DE25 bit and some host msg are already identified.
9 | Product | Frame samples not approval | 2 | 4 | 8 | 2 | 4 | 8 | Delay on SR | Sending samples as soon as possible | Adriano Morais | David Cecilio / Filipe Augusto | Mitigated | 13/07: first samples expected by 17/07 11/08: frames sample scheduled for Aug endind however it is aligned to SR
1 | Product | Either firmware version or hw is not compatible with the way Safra implement QRCode | 3 | 5 | 15 | 3 | 5 | 15 | QRCode is not part of the solution delivered by VF, that can impact on sales revenew | Just during the development it can be clarified. What we need to be prepared is why customer will be reached in case it happens. | Eduardo Quevedo | Marcos Botelho | Accepted | 18/02: Marcos informed by mail - Project Status Report
5 | Development | QR Code implementation via CTLS feature | 4 | 5 | 20 | 4 | 5 | 20 | This feature might be not supported by VF firmware/hardware | Nothing can be do in advance. It will be determined once the code is analized. | Mauricio Bonifacino | Renato Ablas | Cancelled | 02/03: Risks impacts are kept after review with ADC 13/07: No risk anymore
2 | Development | First estimative has been delivered by Setis based on knowledge and feelings as the source code was not delivered in advance. | 2 | 5 | 10 | 2 | 5 | 10 | Some delay for project and also SR posponed | Constantly check meeting with Setis about the progress | Mauricio Bonifacino | Renato Ablas | Cancelled | 02/03: After review the topic with Renato schedule has been kept once there is none clear evidences about what Safra has implemented over the first code delivered by VF. This topic must be reviewed in the same time of project performance. 13/07: Risk has not been presented
4 | Development | Initial PO has estimated without access to either source code or spec from Safra | 3 | 4 | 12 |  |  | 0 | It can result in a CR, aditional costs and time | Weekly meeting with Setis | Mauricio Bonifacino | Renato Ablas | Cancelled | 13/07: Risk was not presented
Note on E4: Mario Abegao Luis de Oliveira: 1: Very Low 2: Low 3: Medium 4: High 5: Very High
Note on G4: Mário Luiz de Oliveira Abegão: 1: Very Low 2: Low 3: Medium 4: High 5: Very High
Note on H4: Mário Luiz de Oliveira Abegão: 1: Very Low 2: Low 3: Medium 4: High 5: Very High

## Opportunities
High Impact
Medium Impact
| Low Impact |  | Next ID: | 2
ID | Area | Description | Probability | Impact | Risk | Prob. Rev | Imp. Rev | Risk. Rev. | Result | Opportunity Maximization | Owner | Responsible | Status | Comments
1 | Certification | Start more than one brand at the same time | 2 | 2 | 4 | 4 | 4 | 16 | Certificatin completed in advance | Negotiationg with Safra about their team take part of the jobs | Mauricion Bonifacino | Mário Abegão / Edson Nascimento | Mitigated | 13/07: Customer has already agreed with this strategy.
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
Note on D4: Mario Abegao Luis de Oliveira: 1: Very Low 2: Low 3: Medium 4: High 5: Very High
Note on E4: Mario Abegao Luis de Oliveira: 1: Very Low 2: Low 3: Medium 4: High 5: Very High
Note on G4: Mário Luiz de Oliveira Abegão: 1: Very Low 2: Low 3: Medium 4: High 5: Very High
Note on H4: Mário Luiz de Oliveira Abegão: 1: Very Low 2: Low 3: Medium 4: High 5: Very High

## BSC
Project Summary
- Version for pilot delivered. Starting SKS package and pilot units production. - Missing ticket (voucher) certification. Impacted by Safra resource unavailable. - Customized frames need to be schedule by Operation Team
Balance Score Card
Perspective | Goals | KPI
Customer | Customer Feedback: Performance, Quality and Planning | 1
Business / Financial | SR Alignment | 5
| Certification Costs(<=10;>10<=20; >20) | 4
| External Development | 5
| Internal Development and/or Support | 5
Internal Process | System Integration Process Alignment | 5
| Risk Management | 5
Risks & Opportunities | Road Blocks | 4
| Opportunities | 5