## Slide 1: Steering Committee Meeting
Sep/2025

## Slide 2: Schedule Review
Planned x Executed: 45% x 30% ( )
Explanation
  Certification phase required 2 additional weeks to be completed. Reason: Bank manage Pin offset in a non standard that required an enhancement in software.
Corrective Action
  UAT deployment will be shortened from 3 weeks to 2 weeks
  PR/DR environment will be deployed in parallel

## Slide 3: Risks Control
Key Management / Exportation
  Issue: Delay noted for productive keys.
  Action Required: Bank needs to align with internal custodians and execute the exportation.
  Target: 15/10/2025.
Virtual Card Feature
  Opportunity: New platform allow virtual card issuance without additional costs to bank.
  Action Required: Bank needs to discuss and align the opportunity with internal team, specially product and operation.
  Suggestion: Implementing virtual cards right now will give competitive advantage to bank and it can start a program like “Virtual First” where customer can start buying as of day 1.
  Target: 15/12/2025

## Slide 4: Changes and Costs Review
New feature for Pin offset will not generate additional costs and will be absorbed by our company
So far none additional Change Request mapped.

## Slide 5: General Topics / Queries
Two additional QA Engineer added into project and will work partial time. The goal is to speed up Pin offset testing. After that these resources will be relocated.

## Slide 6: Thank you!